## Cover
TEST PLAN
Project Name | HKS | Reviewer | HBTT
Project Code |  | Review date | 2019-01-28
Creator | Group 8 | Approver
Version | ver. 1.0 | Approval Date | 2019-01-28
Index
Sheet Name | Description |  | Note
Test Policy
Test Management
Test Strategy
Master Schedule
Reference Document
Name |  | Version | Note
Tài liệu logbug
SRS
Screen Design
Template (Test plan, test report, test case, DefectList, QA)

## Test Policy
Test process policy
Description of policies of testing process.
# | Description | Responsibility | Note
1 | Test report use English or Vietnamese language. | Tester
2 | Làm theo mẫu có sẵn | Test Leader
3 | Tính các test case bằng công thức đúng và hợp lệ | Test Leader
4
Defect should be fixed right away or within 01 day after logging.
Pass/Fail Criteria
The conditions that the testing must satisfy to end test.
# | Criteria | Priority | Note
1 | Test coverage: 90%. | High
2 | Number of test case : 500 | High
3 | Number of test case is pass: 450 | Medium
4 | Number of test case is fail: 50 | Medium

## Test Management
Test Management
Test Scope
Listing of test items in test process.
# | Items | Description |  | Responsibility | Note
1 | Create test cases | Create test case base on Test policy |  | Tester
2 | Create test data | Create test data |  | Tester
7 | Execute system test |  |  | Tester
8 | Report defects, incidents | Report issues, bug report at the end of Testing phase |  | Test Leader
Deliverables
Listing of documents will be delivered of test process.
# | Deliverables | Delivered date | Delivered by | Delivered to | Note
1 | Test plan | 2019-01-23 | Test leader | Customer,PM, Team
2 | Test case | 2019-01-16 | Test leader | Customer,PM, Team
3 | Test Report | 2019-01-18 | Test leader | Customer,PM, Team

## Test Strategy
Test Strategy
Test Objective:
To ensure doesn’t contain serious bugs before release to customer, to confirm that the system has met the requirements
Requirements to be tested
Listing of what is to be tested from the USERS viewpoint of what the system does.
Feature/Function |  | Document which is testing base on |  | Note
• All Functions of the system WebApp described in requirement document |  | HKS Document
Test environment
Listing of environments use in test process.
Type | Environment |  |  | Note
Hardware | PC |  |  | Standard Fsoft
Software | - Chrome latest version
Test stages & techniques
Listing of all test stages of project, and test techniques must be done of every test stages.
Test stage | ST | Method | Name of test tool (if use)
Test Type
Functional Test | x | manual
User Interface Tests | x | manual
Responsibility | Tester
Note on C32: - manual - test tool …

## Master Schedule
Master Schedule
Project Team
Listing of all workers join the testing process
# | Worker / Doer | Position | Responsibilities
1 | Nguyễn Đông Quí | Test leader | Manage Test resource and assign test tasks. Review TC. Create Test report. Support execute test. Create TCs for assigned modules (Chức năng cho người dùng cuối (end-user): thông tin đăng lên cần phải kiểm duyệt, liên lạc). Review test case. Execute test (Chức năng cho người dùng cuối (end-user): thông tin đăng lên cần phải kiểm duyệt, liên lạc). Report test result (Chức năng cho người dùng cuối (end-user): thông tin đăng lên cần phải kiểm duyệt, liên lạc).
2 | Diệp Đại Bảo | Tester | Create TCs for assigned modules (Quản trị hệ thống, Quản lí sự kiện) Review test case Execute test (Quản trị hệ thống, Quản lí sự kiện) Report test result (Quản trị hệ thống, Quản lí sự kiện)
3 | Trịnh Viết Sơn | Tester | Create TCs for assigned modules (Thống kê_thống kê chung, Công cụ hỗ trợ thiết kế_Cơ cấu cam, Cấu hình danh mục) Review test case Execute test (Thống kê_thống kê chung, Công cụ hỗ trợ thiết kế_Cơ cấu cam, Cấu hình danh mục) Report test result (Thống kê_thống kê chung, Công cụ hỗ trợ thiết kế_Cơ cấu cam, Cấu hình danh mục)
4 | Đoàn Công Minh | Tester | Create TCs for assigned modules (Liên hệ góp ý, Tìm việc) Review test case Execute test (Liên hệ góp ý, Tìm việc) Report test result (Liên hệ góp ý, Tìm việc)
5 | Lê Huỳnh Đức | Tester | Create TCs for assigned modules (Quản lý nội dung, Hiển thị nội dung) Review test case Execute test (Quản lý nội dung, Hiển thị nội dung) Report test result (Quản lý nội dung, Hiển thị nội dung)